## Auto plan
Automation plan for the Regression test of Upload features from scratch
Overview | Upload Feature is 100% manual currently and we need a auto plan to automate it. As we don't have any requirement for this product so this plan is made based on my assumption data
Objective | Replace the manual tests for "Upload features" by automation to reduce the effort from QA team and increase the quality
Schedule
Phase 1: Analysis
No | Category | Item(s) | Detail | Output
1 | Product(s) | Roadmap & overall | 'Upload feature' is stable enough? (If this feature will be changed in the roadmap, should not auto it, focus on stable features/TCs that give value) New support platforms (if this feature will support more platforms so notice them in the Test tool selection to scale in the future) Priority of this feature and its components | List of items to automate: - Features/Components - TCs - Priority List of Env for auto to support
2 |  | Scope of test | Test Env Functional tests (UI, integration, API, services…) Non function tests (performance, security, usability…) CI/CD support?
3 | Team capabilities | Domains and resources | Team knowledge (auto skills set) Current bandwidth (How many resources are busy with current releases and available for auto) | Plan for automation items and schedule Test objective Team responsibilities and composition
4 |  | QA Data | Review these items: Manual TCs list of Upload feature and its quality to see if they are ready for auto or not Current test coverage Regression time for each test cycle
5 | Risks | Release schedule | Release schedule is tight and affect the auto plan | ROI of auto plan compared with manual before
6 |  | Resources | Lack of auto resources or skills | Training or hiring plan to adapt the auto tasks
7 |  | Cost | Limit budget will be spent for auto | Scale the auto plan within the budget provided or raise more if necessary
Phase 2: Test tools selection
1 | Auto approach | Open source or Enterprise | Base on the product needs, evaluate some tools that represent for open source and enterprise. For ex: Selenium and it's eco system for Open source. Katalon, Eggplants, TestArchitect… for Enterprise | The pros and cons, cost of each solution and tool if using for this project. This data will be used to discuss with management team to have final decision
2 | Tools selection | Test fw used | Select the test fw to apply based on project target | Base on the result of above items, provide the test fw and tools using with demo data
3 |  | Test tools used | Select the test tool to apply based on project target (e.g. support integration for CI/CD, Jira…)
Phase 3: Execution plan
1 | Auto schedule | Design test fw | Test structure and all common libs needed that apply for whole project
2 |  | Scripting | Implement all scripts needed to automate the features
3 |  | Execution | Execute process for define scripts (daily, release, impact…)
4 |  | Reporting | Results and report auto status | Results and report auto status
5 | Integration support | CI/CD integration | Should make another plan as it needs many discussions with DevOps team for the pipeline | Capabilities to integrate all the tests to CI/CD pipeline and define the working process (run process, bugs alert, email notification…)
6 |  | Jira, Jenskin, Source management… | Base on the project fw that is using (Jira, TestRail…) to define the scope of support (bug links, user stories implementation…) | Capabilities to integrate the tests to team fw
Phase 4: Maintainance and improvement plan
1 | Maintance | Running process and report | Keep running and reports for product maintaince
2 |  | Keep scripts up to date | Plan to update scripts whenever the design/TCs change
3 | Improvement | Stability | Improve scripts to handle unstable issues and errors handling
4 |  | Results | Store all needed info for debug and raise bugs
5 |  | Scripts fixed looping | Fix all things related to scripts
6 |  | Other integration | Base on project needs, integrate the scripts to others